## Product Backlog
User_Story_ID | Description | Acceptance Criteria | Priority | Validation | Point | assign
US_01 | User should be able to use Citizenships Page functionality | User should be able to create new citizionships with required informations | High | UI and Backend Testing
User should be able to update an existant citizenship
User should be able to delete an existant citizenship
User should not be able to delete non existant citizenship
US_02 | User should be able to use Nationalities Page functionality | User should be able to create new Nationalites | High | UI and Backend Testing
User should be able to update an existant Nationality
User should be able to delete an existant Nationality
User should not be able to create a Nationality that is exists with similar name
US_03 | User should be able to use Fees Page functionality | User should be able to create a new Fee Type | High | UI and Backend Testing
User should be able to update an existant Fee Type
User should be able to delete an existant Fee Type
User should be able to search an Fee Type
US_04 | User should be able to use Discounts Page functionality | User should be able to create a new Discount | High | UI and Backend Testing
User should be able to update an existant Discount
User should be able to delete an existant Discount
US_05 | User should be able to use Grade Levels Page functionality | User should be able to create a Grade Level | High | UI and Backend Testing
User should be able to update an existant Grade Level
User should be able to delete an existant Grade Level
US_06 | User should be able to use Document Types Page functionality | User should be able to view Document Types Page | High | UI and Backend Testing
User should be able to create new Document and view successfully validating the message
User should be able to delete Documentand and view successfully validating the message
User should be able to edit Document and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_07 | User should be able to use Notifications Page functionality (Messaging) | User should be able to view Notifications Page | High | UI and Backend Testing
User should be able to create new Notification and view successfully validating the message
User should be able to delete Notification and view successfully validating the message
User should be able to edit Notification and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_08 | User should be able to use Item Categories Page functionality. (Inventory-Setup) | User should be able to view Item Categories Page | High | UI and Backend Testing
User should be able to create new Item Categorie and view successfully validating the message
User should be able to delete Item Categorie and view successfully validating the message
User should be able to edit Item Categorie and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_09 | User should be able to use Budget Projects Page functionality.(Budget-Setup) | User should be able to view Budget Projects page | High | UI and Backend Testing
User should be able to Budget Project and view successfully validating the message
User should not be able to add without Code
User should be able to delete Budget Project and view successfully validating the message
US_10 | User should be able to Item Budgets functionality.(Budget) | User should be able to view Budgets page | High | UI and Backend Testing
User should be able to create Budgets and view successfully validating the message
User should not be able to add without Year,Budget Group and School
User should be able to delete Budgets and view successfully validating the message
US_11 | User should be able to use Notation Keys Page functionality | User should be able to view Notation Keys page | High | UI and Backend Testing
User should be able to create a Notation Key and view successfully validating the message
User should be able to edit Notation Key and view successfully validating the message
User should be able to delete Notation Key and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_12 | User should be able to use Attestations Page functionality | User should be able to view Attestations page | High | UI and Backend Testing
User should be able to create an Attestation and view successfully validating the message
User should be able to edit Attestation and view successfully validating the message
User should be able to delete Attestation and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_13 | User should be able to use Position Categories Page (Human Resources) functionality | User should be able to view Position Categories page | High | UI and Backend Testing
User should be able to create Position Categories and view successfully validating the message
User should be able to edit Position Categories and view successfully validating the message
User should be able to delete Position Categories and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_14 | User should be able to use Dismissal Articcles Page functionality | User should be able to view Dismissal Articles page | High | UI and Backend Testing
User should be able to create Dismissal Articles and view successfully validating the message
User should be able to edit Dismissal Articles and view successfully validating the message
User should be able to delete Dismissal Articles and view successfully validating the message
When searching by name , the results should be matched the search terms.
User story numbers: | 14
Minimum test case: | 56

## Beklentiler
Takimlardan Beklenilenler
1 | Tester | Basqar projesi ile alakali tum gereklilikler anlasilmali ve Acceptance criteria lar tamamlanmalidir.(TEST CASE)
2 | ORHAN BY | Projede Cucumber frameworku kullanilmalidir.
3 | ORHAN BY | Framework team lead tarafindan Github a konulmali ve kodlar gun gun githubdan guncellenerek proje yurutulmelidir
4 | tester | Tüm ekip üyeleri kendi ile alakali user story lerde bulunan her bir accaptance criteria icin en az bir test case yazmali
5 | tester | Tüm ekip üyeleri test caselerini Jira ya girmeli ve manuel olarak burada execution lari yapmali
6 | tester | Tüm ekipler demo meetinglerde sunumlarini yapacaklar
7 | ? | Tüm toplantilar ve calismalar video kaydi alinarak yapilmaya calisilacak. Toplanti notlari kararlari yazilarak takip edilecek

## Proje Takvim
Dönem | Tarih |  | Toplanti | Aciklama
Sprint oncesi | 2020-11-28 | Cumartesi | First Grooming Session (First Sprint) | Tüm User Story ler Product Owner tarafindan Scrum ekibine aciklanir ve anlasilmayan yerler acikliga kavusturulur. Team kapasitesi goz onune alarak Backlaga bu sprint icin alinacak user storyler belirlenir. | Gruplar da scrum master, product owner, ve team lead belirlenmeli, sorumluluklar dagitilmali
| 2020-11-29 | Pazar | Team lead meeting
Sprint 1 | 2020-11-30 | Pazartesi | First Sprint Planning Meeting | Scrum Master toplantiyi yonetir. User Storyler Scrum team tarafindan puanlanir ve paylasimlari yapilir.
| 2020-12-01 | Salı | Daily Stand-up | her gun 15 dk olacak sekilde dun ne yapildigi ve bu gun ne yapilacaginin konusuldugu toplanti
| 2020-12-02 | Çarşamba | Daily Stand-up
| 2020-12-03 | Perşembe | Daily Stand-up
| 2020-12-04 | Cuma | Daily Stand-up
| 2020-12-05 | Cumartesi | Hafta Sonu Tatili
| 2020-12-06 | Pazar
| 2020-12-07 | Pazartesi | Daily Stand-up
| 2020-12-08 | Salı | Daily Stand-up
| 2020-12-09 | Çarşamba | Second Grooming Session (Upcoming Sprint) | Kalan User Story ler Product Owner tarafindan Scrum ekibine aciklanir ve anlasilmayan yerler acikliga kavusturulur.
| 2020-12-10 | Perşembe | Daily Stand-up
| 2020-12-11 | Cuma | First Demo meeting (review meeting / All teams) | Tum gruplar ilk sprint icin projeyi nasil islettiklerini anlatacak ve testlerinden bir kismini calistirarak sunum yapacaklar
| 2020-12-12 | Cumartesi | Hafta Sonu Tatili
| 2020-12-13 | Pazar
Sprint 2 | 2020-12-14 | Pazartesi | Second Sprint Planning meeting | Scrum Master toplantiyi yonetir. User Storyler Scrum team tarafindan puanlanir ve paylasimlari yapilir
| 2020-12-15 | Salı | Daily Stand-up
| 2020-12-16 | Çarşamba | First Retrospective Meeting | Takim kendi icinde ilk sprinti degerledirir.neler iyi gitti neler gelistirlebilir gibi..
| 2020-12-17 | Perşembe | Daily Stand-up
| 2020-12-18 | Cuma | Daily Stand-up
| 2020-12-19 | Cumartesi | Hafta Sonu Tatili
| 2020-12-20 | Pazar
| 2020-12-21 | Pazartesi | Daily Stand-up
| 2020-12-22 | Salı | Daily Stand-up
| 2020-12-23 | Çarşamba | Daily Stand-up
| 2020-12-24 | Perşembe | Daily Stand-up
| 2020-12-25 | Cuma | Second Demo meeting (review meeting / All teams) | Tum gruplar ikinci sprint icin projeyi nasil islettiklerini anlatacak ve testlerinden bir kismini calistirarak sunum yapacaklar
Sprint Sonrasi | 2020-12-26 | Cumartesi | Hafta Sonu Tatili
| 2020-12-27 | Pazar
| 2020-12-28 | Pazartesi | Final Retrospective Meeting | Takim kendi icinde ilk sprinti degerledirir.neler iyi gitti neler gelistirlebilir gibi..

## Retrospective
Retrospective Meeting Evaluation |  |  |  | Description
Neler iyi gitti? | Neler geliştirilebilir? | Bir sonraki sprint için ne yapacağız? | Herhangi bir engelle karşılaştın mı? | Tüm ekip üyeleri fikirlerini soylemelidir

## Sayfa1
Jira: | https://www.atlassian.com/software/jira
Jira Xray: | https://marketplace.atlassian.com/apps/1211769/xray-test-management-for-jira?hosting=cloud&tab=overview

## Test Case
User Story ID | Test Case ID | Test Objective | Pre-Condition | Steps | Test Data | expected step result | Expected Result | Actual Result | Status
US 0005 | TC_0001 | User should be able to view Position Salary page | user must be logged in | Navigate to https://test.basqar.techno.study/ | Url=https://test.basqar.techno.study/ | User shoud be able to see homepage | when we click on Position salary, we should be able to see Psition Salary Page | when we clicked on Position salary, we saw Psition Salary Page | passed
|  |  |  | login https://test.basqar.techno.study/ | user name=daulet2030@gmail.com | User shoud be able to login
|  |  |  | click on Human Resources | password=TechnoStudy123@ | Human Resources should be clickable
|  |  |  | click on Setup |  | Setup should be clickable
click on Position salary
US 0005 | TC_0002 | User should be able to create Position Salary and view successfully validating the message | user must be logged in | Navigate to https://test.basqar.techno.study/ | Url=https://test.basqar.techno.study/ |  | When we click the Save button, we should be able to see the message that the new position has been successfully created. | When we clicked the Save button, we saw the message that the new position has been successfully created. | passed
|  |  |  | login https://test.basqar.techno.study/ | user name=daulet2030@gmail.com
|  |  |  | click on Human Resources | password=TechnoStudy123@
|  |  |  | click on Setup | name=technostudy
click on Position Salary
click on Add Position Salary
type name on Name box
click on Save button

## Product Backlog sahibinden
User_Story_ID | Description (USER STORY : SCRUM MASTER) | Acceptance Criteria(TEST CASE : TESTER ) | Priority (ÖNCELİK) | Validation (DOĞRULAMA) | Point (GÖREV SÜRESİ) | assign (GÖREVLİ)
US_01 | User should be able to use Citizenships Page functionality (Kullanıcı, Vatandaşlık Sayfası işlevini kullanabilmelidir) | User should be able to create new citizionships with required informations (Kullanıcı gerekli bilgilerle yeni vatandaşlıklar oluşturabilmelidir) | High | UI and Backend. (KULLANICI ARAYÜZÜ VE API ,DB ) Testing | 5 | HALUK BİLGİN
User should be able to update an existant citizenship (Kullanıcı, mevcut bir vatandaşlığı güncelleyebilmelidir)
User should be able to delete an existant citizenship (Kullanıcı, mevcut bir vatandaşlığı silebilmelidir)
User should not be able to delete non existant citizenship (Kullanıcı, var olmayan vatandaşlığı silememelidir)
US_02 | User should be able to use ELECTRONIC PRODUCTS Page functionality. (Kullanıcı, ELEKTRONIK ÜRÜNLERİ Sayfası işlevini kullanabilmelidir) | User should be able to create new COMPUTERS (Kullanıcı yeni BİLGİSAYAR oluşturabilmelidir) | High | UI and Backend. (KULLANICI ARAYÜZÜ VE SON KULLANICI) Testing | 6 | ORHAN BEY
User should be able to update an existant COMPUTER (Kullanıcı, mevcut bir BİLGİSAYARI güncelleyebilmelidir)
User should be able to delete an existant COMPUTER (Kullanıcı, mevcut bir BİLGİSAYARI silebilmelidir)
User should not be able to create a COMPUTER that is exists with similar name (Kullanıcı, benzer adla var olan bir BİLGİSAYAR oluşturamamalıdır)
US_03 | User should be able to use TEXTILE PRODUCTS Page functionality (Kullanıcı, TEKSTİL ÜRÜNLERİ Sayfası işlevini kullanabilmelidir) | User should be able to create a new Fee Type | High | UI and Backend Testing
User should be able to update an existant Fee Type
User should be able to delete an existant Fee Type
User should be able to search an Fee Type
US_04 | User should be able to use Discounts Page functionality | User should be able to create a new Discount | High | UI and Backend Testing
User should be able to update an existant Discount
User should be able to delete an existant Discount
US_05 | User should be able to use Grade Levels Page functionality | User should be able to create a Grade Level | High | UI and Backend Testing
User should be able to update an existant Grade Level
User should be able to delete an existant Grade Level
US_06 | User should be able to use Document Types Page functionality | User should be able to view Document Types Page | High | UI and Backend Testing
User should be able to create new Document and view successfully validating the message
User should be able to delete Documentand and view successfully validating the message
User should be able to edit Document and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_07 | User should be able to use Notifications Page functionality (Messaging) | User should be able to view Notifications Page | High | UI and Backend Testing
User should be able to create new Notification and view successfully validating the message
User should be able to delete Notification and view successfully validating the message
User should be able to edit Notification and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_08 | User should be able to use Item Categories Page functionality. (Inventory-Setup) | User should be able to view Item Categories Page | High | UI and Backend Testing
User should be able to create new Item Categorie and view successfully validating the message
User should be able to delete Item Categorie and view successfully validating the message
User should be able to edit Item Categorie and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_09 | User should be able to use Budget Projects Page functionality.(Budget-Setup) | User should be able to view Budget Projects page | High | UI and Backend Testing
User should be able to Budget Project and view successfully validating the message
User should not be able to add without Code
User should be able to delete Budget Project and view successfully validating the message
US_10 | User should be able to Item Budgets functionality.(Budget) | User should be able to view Budgets page | High | UI and Backend Testing
User should be able to create Budgets and view successfully validating the message
User should not be able to add without Year,Budget Group and School
User should be able to delete Budgets and view successfully validating the message
US_11 | User should be able to use Notation Keys Page functionality | User should be able to view Notation Keys page | High | UI and Backend Testing
User should be able to create a Notation Key and view successfully validating the message
User should be able to edit Notation Key and view successfully validating the message
User should be able to delete Notation Key and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_12 | User should be able to use Attestations Page functionality | User should be able to view Attestations page | High | UI and Backend Testing
User should be able to create an Attestation and view successfully validating the message
User should be able to edit Attestation and view successfully validating the message
User should be able to delete Attestation and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_13 | User should be able to use Position Categories Page (Human Resources) functionality | User should be able to view Position Categories page | High | UI and Backend Testing
User should be able to create Position Categories and view successfully validating the message
User should be able to edit Position Categories and view successfully validating the message
User should be able to delete Position Categories and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_14 | User should be able to use Dismissal Articcles Page functionality | User should be able to view Dismissal Articles page | High | UI and Backend Testing
User should be able to create Dismissal Articles and view successfully validating the message
User should be able to edit Dismissal Articles and view successfully validating the message
User should be able to delete Dismissal Articles and view successfully validating the message
When searching by name , the results should be matched the search terms.
User story numbers: | 14
Minimum test case: | 56

## US_01 Test Case
User Story ID | Test Case ID | Test Objective | Pre-Condition | Steps | Test Data | expected step result | Expected Result | Actual Result | Status
US_01 | TC_01 | User should be able to create new citizionships with required informations | user must be logged in | Navigate to https://test.basqar.techno.study/ | Url=https://test.basqar.techno.study/ | User should be able to see homepage | when we clicked on Citizenship, we saw Citizenship Page and we should be able to see the message that the new Citizenship has been successfully CREATED. | when we clicked on Citizenship, we saw Citizenship Page and we saw the message that the new Citizenship has been successfully CREATED. | passed
|  |  |  | login https://test.basqar.techno.study/ | user name=daulet2030@gmail.com. password=TechnoStudy123@ | User should be able to login. Citizenship should be clickable
|  |  |  | click on Setup |  | Setup should be clickable
|  |  |  | click on Parameters |  | Parameters should be clickable
|  |  |  | click on Citizenships |  | Citizenships should be clickable
|  |  |  | click on Add Button | Name=HalUk. Short Name=Vicdan | Add Button should be clickable
|  |  |  | click on Save Button |  | Save Button should be clickable
US_01 | TC_02 | User should be able to update an existant citizenship | user must be logged on Citizenship page | Navigate to https://test.basqar.techno.study/ | Url=https://test.basqar.techno.study/ | User shoud be able to see homepage | when we clicked on Citizenship, we saw Citizenship Page and we should be able to see the message that the new Citizenship has been successfully UPDATED. | when we clicked on Citizenship, we saw Citizenship Page and we saw the message that the new Citizenship has been successfully UPDATED. | passed
|  |  |  | login https://test.basqar.techno.study/ | user name=daulet2030@gmail.com. password=TechnoStudy123@ | User should be able to login. Citizenship should be clickable
|  |  |  | click on Setup |  | Setup should be clickable
|  |  |  | click on Parameters |  | Parameters should be clickable
|  |  |  | click on Citizenships |  | Citizenships should be clickable
|  |  |  | click on Name Button | Name=HalUk | Add Button should be clickable
|  |  |  | click on Short Name Button | Short Name=Vicdan | Name Short Name should be clickable
|  |  |  | click on Search Button |  | Search Button should be clickable
|  |  |  | click on Edit Button | Name=HalUkBilgin Short Name=Vicdanli | Edit Button should be clickable
|  |  |  | click on Save button |  | Save Button should be clickable
US_01 | TC_03 | User should be able to delete an existant citizenship | user must be logged on Citizenship page | Navigate to https://test.basqar.techno.study/ | Url=https://test.basqar.techno.study/ | User shoud be able to see homepage | when we clicked on Citizenship, we saw Citizenship Page and we should be able to see the message that the new Citizenship has been successfully DELETED. | when we clicked on Citizenship, we saw Citizenship Page and we saw the message that the new Citizenship has been successfully UPDATED. | passed
|  |  |  | login https://test.basqar.techno.study/ | user name=daulet2030@gmail.com. password=TechnoStudy123@ | User shoud be able to login. Human Resources should be clickable
|  |  |  | click on Setup |  | Setup should be clickable
|  |  |  | click on Parameters |  | Parameters should be clickable
|  |  |  | click on Citizenships |  | Citizenships should be clickable
|  |  |  | click on Name Button | Name=HalUkBilgin | Add Button should be clickable
|  |  |  | click on Short Name Button | Short Name=Vicdanli | Name Short Name should be clickable
|  |  |  | click on Search Button |  | Search Button should be clickable
|  |  |  | click on Delete Button |  | Delete Button should be clickable
|  |  |  | click on Yes Button |  | Yes Button should be clickable
US_01 | TC_04 | User should not be able to delete non existant citizenship | user must be logged on Citizenship page | Navigate to https://test.basqar.techno.study/ | Url=https://test.basqar.techno.study/ |  | When we click the Save button, we should be able to see the message that the new position has been successfully created. | When we clicked the Save button, we saw the message that the new position has been successfully created. | passed
|  |  |  | login https://test.basqar.techno.study/ | user name=daulet2030@gmail.com
|  |  |  | click on Human Resources | password=TechnoStudy123@
|  |  |  | click on Setup | name=technostudy
click on Position Salary
click on Add Position Salary
type name on Name box
click on Save button

## Product Backlog (group_2)
User_Story_ID | Description | Acceptance Criteria | Priority | Validation | Point | assign
US_01 | User should be able to use Citizenships Page functionality | User should be able to create new citizionships with required informations | High | UI and Backend Testing | 5 | HALUK B
User should be able to update an existant citizenship
User should be able to delete an existant citizenship
User should not be able to delete non existant citizenship
US_02 | User should be able to use Nationalities Page functionality | User should be able to create new Nationalites | High | UI and Backend Testing | 5 | FERAH H
User should be able to update an existant Nationality
User should be able to delete an existant Nationality
User should not be able to create a Nationality that is exists with similar name
US_03 | User should be able to use Fees Page functionality | User should be able to create a new Fee Type | High | UI and Backend Testing | 5 | VOLKAN B
User should be able to update an existant Fee Type
User should be able to delete an existant Fee Type
User should be able to search an Fee Type
US_04 | User should be able to use Discounts Page functionality | User should be able to create a new Discount | High | UI and Backend Testing | 5 | SARE H
User should be able to update an existant Discount
User should be able to delete an existant Discount
US_05 | User should be able to use Grade Levels Page functionality | User should be able to create a Grade Level | High | UI and Backend Testing | 5 | SARE H
User should be able to update an existant Grade Level
User should be able to delete an existant Grade Level
US_06 | User should be able to use Document Types Page functionality | User should be able to view Document Types Page | High | UI and Backend Testing | 5 | METİN B
User should be able to create new Document and view successfully validating the message
User should be able to delete Documentand and view successfully validating the message
User should be able to edit Document and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_07 | User should be able to use Notifications Page functionality (Messaging) | User should be able to view Notifications Page | High | UI and Backend Testing |  | ORHAN B
|  | User should be able to create new Notification and view successfully validating the message |  |  | 5
User should be able to delete Notification and view successfully validating the message
User should be able to edit Notification and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_08 | User should be able to use Item Categories Page functionality. (Inventory-Setup) | User should be able to view Item Categories Page | High | UI and Backend Testing | 5 | ÖZGE H
User should be able to create new Item Categorie and view successfully validating the message
User should be able to delete Item Categorie and view successfully validating the message
User should be able to edit Item Categorie and view successfully validating the message
When searching by name, the results should be matched the search terms.
US_09 | User should be able to use Budget Projects Page functionality.(Budget-Setup) | User should be able to view Budget Projects page | High | UI and Backend Testing | 8 | METİN B
|  | User should be able to Budget Project and view successfully validating the message |  |  | 8
User should not be able to add without Code
User should be able to delete Budget Project and view successfully validating the message
US_10 | User should be able to Item Budgets functionality.(Budget) | User should be able to view Budgets page | High | UI and Backend Testing | 8 | ORHAN B
User should be able to create Budgets and view successfully validating the message
User should not be able to add without Year,Budget Group and School
User should be able to delete Budgets and view successfully validating the message
US_11 | User should be able to use Notation Keys Page functionality | User should be able to view Notation Keys page | High | UI and Backend Testing | 5 | HALUK B
User should be able to create a Notation Key and view successfully validating the message
User should be able to edit Notation Key and view successfully validating the message
User should be able to delete Notation Key and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_12 | User should be able to use Attestations Page functionality | User should be able to view Attestations page | High | UI and Backend Testing | 5 | FERAH H- HATİCE H
User should be able to create an Attestation and view successfully validating the message
User should be able to edit Attestation and view successfully validating the message
User should be able to delete Attestation and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_13 | User should be able to use Position Categories Page (Human Resources) functionality | User should be able to view Position Categories page | High | UI and Backend Testing | 5 | VOLKAN B
User should be able to create Position Categories and view successfully validating the message
User should be able to edit Position Categories and view successfully validating the message
User should be able to delete Position Categories and view successfully validating the message
When searching by name , the results should be matched the search terms.
US_14 | User should be able to use Dismissal Articcles Page functionality | User should be able to view Dismissal Articles page | High | UI and Backend Testing | 5 | ÖZGE H
User should be able to create Dismissal Articles and view successfully validating the message
User should be able to edit Dismissal Articles and view successfully validating the message
User should be able to delete Dismissal Articles and view successfully validating the message
When searching by name , the results should be matched the search terms.
User story numbers: | 14
Minimum test case: | 56